## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 67% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 38% | 30% | 7.5% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.
Budget |  | Money ($M) | Actual ($M) | Future ($M)
| M1 | 20 | 22 | 22
| M2 | 50 | 55 | 55
| M3 | 75 | 80 | 80
| M4 | 100 | 110 | 100
| M5 | 120 | 90 | 125

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| KPIs: Monthly Track Installation Progress ; Electrification Infrastucture Completion Rate; Community Engagement Index; Other: Refer to the notes on the left side. |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
[5 empty] | Phase 2 | [6 empty] | ←Illustrative of the Timeline
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [8 empty] | Project Financials
| Status Update |  | Challenges
| *Electrification:* 30 miles of track have been electrified out of the 68 miles planned for Phase 1. *Track Installation:* 6 miles have been completed in the Eastern Section (out of 12 miles planned) and 10 miles in the Southeastern Quadrant (out of 15 miles planned). *Community Engagement:* The community has responded positively to the project’s transparency and engagement efforts, building trust and appreciation for the project. *Efficiency Improvement:* Equipment upgrades in the Southeastern Quadrant have resulted in improved installation efficiency. |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| Community Feedback Highlights |  |  | *Eastern Section Delay:* The Eastern Section faces a risk due to the rocky terrain, which has delayed progress by 6 miles. To address this, an alternative construction method is being evaluated. *Overspent in Excavation:* The excavation costs in the Eastern Section exceeded projections, but savings from material costs have offset this, keeping the overall budget within 5% of projections for this phase. *Substations Delay:* There are delays in the construction of substations due to issues with electrical components. An action plan is in progress with the buyer to address these delays.
Residents have expressed gratitude for the consistent engagement, which has fostered transparency in communication to voice concerns and building trust with the project and the community.
Noise Concerns due to a rise in complaints about nighttime construction noise in the Eastern Section has been reported and residents requested the work be limited to daytime hours to reduce disturbance.
Current Progress: The project has successfully electrified 30 miles of track out of the 68 miles planned for Phase 1.
Challenges: There has been a delay in the Eastern Section due to rocky terrain, causing a 6-mile delay in the progress. An alternative method is currently being evaluated to expedite progress.
Current Spending: The project has spent 90M to date.
Projected Overbudget: The project is tracking to be slightly overbudget, with a total projected spend of 125M due to unforeseen costs related to terrain challenges in the Eastern Section.
Notes:
30 miles electrified out of 68 miles (44% completed).
6 miles installed out of 12 miles (50% completed).
10 miles installed out of 15 miles (67% completed).
Current expenditure is 90M, with a projected total cost of 125M.
Positive feedback from the community regarding transparency and involvement, but concerns about nighttime construction noise persist.